## Shelby_Open_Tickets
Issue | Description | Deliverable | Owner | Notes
4 | TNshelby - The 6 month report has not been correctly received from county. | DTS | Christy | Will distribute Functional Requirement for approval.
10 | confirm the Early Vote application | Early Vote | Christy | Early/vote and VC Programmer Issue
26 | TN - Unable to run the voter statistics turnout reports on their main voter server. (Ok to close) | RPL | Dennis | Close ticket
29 | Bar code readers will not read the bar codes off any of the absentee ballot labels | RPL | Christy | Queue for delivery
30 | Early vote sites are reporting that they are randomly not able to click on the 'Print Application' and/or 'Cast Vote' buttons. | Other | Christy | Close ticket
31 | TN - Sporadically unable to log into ESM after shutting down their old SQL server. | Other | Christy | Close ticket
32 | TN - The Poll worker summary report (ie: Poll Worker Payment Type Totals - 00000-POW-007-C report ) is not balancing with the Poll Worker Detailed Report | RPL | Christy | Close ticket
40 | TN - Unable to generate poll worker payments using the DTS Payments export. | RPL | Christy | Close ticket
41 | TN - Somehow poll workers are showing up as being paid twice according to the Poll Worker Payment Listing by Election Precint | RPL | Christy | Close ticket
48 | TN - Wanting to know how they can change the body of a poll worker correspondence letter that is automatically generated within ESM | Other | Christy | Research source of phone number and provide options. Is this a data or report change?
54 | TN - Question regarding the 'Other' code on the Election Turn Out Statisics Reports. | Other | Christy | Review if all other race codes will be counted by the Other totals. Will new codes follow this as well?
60 | Permanent Absentee Voters in early vote it is not showing the designation that they are a Permanent Absentee Voter. (Ok to close) | ESM | Dennis | Close ticket
71 | Issue with looking up a voter history (Ok to close) | Early Vote | Dennis | Close ticket
72 | The Client is unable to use the make changes button on the Alternate address button | ESM | Christy | Close ticket
79 | client called stating that when they attempt to create a Precinct Personnel Report, Poll Workers> Precinct Personnel Assignments, it is not showing Democrat registers | RPL | Christy | Queue for delivery
84 | In participation voter listing for election for the 2004 primary election, random voters are showing that they voted 3 times in the primary election. | Other | Christy | Close ticket
86 | Modify report# 00000-VOT-008-C " Voter Applications Statistics" to display the options criteria used to generate the report under the report name (title). | RPL | Christy | Queue for delivery
87 | Voter #1035571 voted absentee, but is included in early vote totals on the Early Vote Daily Total Report. | Other | Christy | Close ticket
95 | Create new export (separate menu item) that will be used for GIS analysis. | RPL | Christy | Queue for delivery
96 | Receiving SQL error "String or binary data will be truncated" when trying to process a change of address application. | ESM | Dennis | Reported that Problem still exists
102 | Registration/ID card is truncating the Registration date if the Reg Date is a 10 character field | RPL | Christy | Queue for delivery
103 | TN - Table link issue with Incorrect Block Ranges Report | Other | Christy | Leave open until we confirm that Shelby will accept a new version of ESM. That version would contain incorporated cleanup reports.
104 | TN - Error when creating an election and pull in worker (Ok to close) | ESM | Christy | Close ticket
109 | TN - The participating voter listing report is now truncating the last digit of the voter's id numbers | ESM | Christy | Queue for delivery
129 | Provide method for distinguishing badges for officers from other poll workers.(Ok to close) | RPL | Christy | Close ticket